## P&L
New Conference 2027
April 6-8, 2027 ¦ Los Angeles, CA ¦ 3 event days + 1 set-up ¦ 9 months planning
PROPOSAL SUMMARY
| ITEM | CLIENT COST | OUR COST | NET PROFIT | % Profit
| Project Hours (568) | 48830 | 32244 | 16586 | 33.97%
| Onsite Management (224) | 20120 | 12336 | 7784 | 38.69%
| Staff Overhead ($0.61 / staff hour) | 0 | 483.12 | -483.12
| TOTALS | 68950 | 45063.12 | 23886.88 | 34.64%
| Admin Fee (2.0%) | 1379 | 0 | 1379
| Less Multi-Year Discount (5.0%) | 0 | 0 | 0
| GRAND TOTAL | 70329 | 45063.12 | 25265.88 | 35.93%
PRE-PLANNING HOURS BY STAFF CATEGORY
| CATEGORY | HOURS | OUR RATE / HR | OUR COST | STAFF COUNT | HRS / PERSON / WEEK
| Managers | 336 | 60 | 20160 | 1 | 8.6154
| Coordinators | 193 | 42 | 8106 | 1 | 4.9487
| Team (weekly meetings) | 39 | 102 | 3978 | 2 | 1
| TOTAL PRE-PLANNING | 568 |  | 32244 | 2
HRS / PERSON / WEEK is the workload check — above roughly 10, add staff or trim scope.
EVENT MANAGEMENT
| SCOPE OF WORK | CLIENT RATE | HOURS | CLIENT COST | OUR RATE | HOURS | OUR COST | NET PROFIT | % Profit
PM/EC | PLANNING, TIMELINE & COMMUNICATIONS | 102.48 | 125 | 12810 | 67.488 | 125 | 8436 | 4374 | 34.15%
PM | VENUE MANAGEMENT | 90 | 40 | 3600 | 60 | 40 | 2400 | 1200 | 33.33%
PM | EVENT BRANDING | 90 | 45 | 4050 | 60 | 45 | 2700 | 1350 | 33.33%
PM | FOOD & BEVERAGE | 90 | 34 | 3060 | 60 | 34 | 2040 | 1020 | 33.33%
EC | REGISTRATION | 65 | 82 | 5330 | 42 | 82 | 3444 | 1886 | 35.38%
EC | THIRD PARTY VENDORS | 65 | 40 | 2600 | 42 | 40 | 1680 | 920 | 35.38%
PM | STAFF MANAGEMENT | 90 | 14 | 1260 | 60 | 14 | 840 | 420 | 33.33%
EC | SPONSORSHIPS | 65 | 32 | 2080 | 42 | 32 | 1344 | 736 | 35.38%
PM | PROGRAMMING | 90 | 63 | 5670 | 60 | 63 | 3780 | 1890 | 33.33%
PM | FINANCIAL MANAGEMENT | 90 | 18 | 1620 | 60 | 18 | 1080 | 540 | 33.33%
PM | EXHIBIT MANAGEMENT | 90 | 60 | 5400 | 60 | 60 | 3600 | 1800 | 33.33%
PM | POST-EVENT | 90 | 15 | 1350 | 60 | 15 | 900 | 450 | 33.33%
| TOTALS |  | 568 | 48830 |  | 568 | 32244 | 16586 | 33.97%
ONSITE MANAGEMENT
| SCOPE OF WORK | CLIENT RATE | HOURS | CLIENT COST | OUR RATE | HOURS | OUR COST | NET PROFIT | % Profit
PM | Project Manager | 100 | 48 | 4800 | 60 | 48 | 2880 | 1920 | 40%
PM | Event Manager | 100 | 48 | 4800 | 60 | 48 | 2880 | 1920 | 40%
PM | Executive Producer | 100 | 48 | 4800 | 60 | 48 | 2880 | 1920 | 40%
EC | Event Coordinator | 65 | 32 | 2080 | 42 | 32 | 1344 | 736 | 35.38%
EC | Registration Coordinator | 65 | 32 | 2080 | 42 | 32 | 1344 | 736 | 35.38%
EC | Coordinator Overtime (2 x 2 hrs x 4 days) | 97.5 | 16 | 1560 | 63 | 16 | 1008 | 552 | 35.38%
| TOTALS |  | 224 | 20120 |  | 224 | 12336 | 7784 | 38.69%
STAFF OVERHEAD
| ITEM | STAFF HOURS | RATE / HR | OVERHEAD COST
| Pre-planning staff hours | 568 | 0.61 | 346.48
| Onsite staff hours (incl. overtime) | 224 | 0.61 | 136.64
| TOTAL STAFF OVERHEAD | 792 |  | 483.12
Overhead is a CTC cost — not billed, so it comes out of margin. The admin fee is charged on top of the client subtotal.

## INPUTS
CTC CONFERENCE P&L BUILDER — INPUTS
Type in the yellow cells only. Choose the scope of work on the SCOPE tab. The P&L tab is all formulas — nothing to fill in there.
1. EVENT PROFILE
Event / Client Name | New Conference 2027
Event Dates (display text) | April 6-8, 2027
Location | Los Angeles, CA
2. EVENT SIZE
Attendees | 500 | Main driver of the Event Scale Index below
Exhibitors | 60 | Exhibit Management bills at 1 hour per exhibitor
Sponsors | 20 | Sponsor Management bills at 1 hour per sponsor
Speakers | 15 | Speaker Management bills at 1 hour per speaker, split prep / onsite
Third-Party Vendors to Source | 5 | Third Party Vendors bills at 5 hours per vendor sourced
Site Visits | 1 | Site Visits bills at 10 hours each (travel, walk-through, write-up)
3. SCHEDULE
Event Days | 3
Set-Up / Load-In Days | 1
Travel Days | 0
TOTAL ONSITE DAYS | 4
Months of Pre-Planning | 9 | Months from contract signature to day 1 of the event
Planning Weeks | 39 | Weekly meetings, the project management system and approvals key off this
EVENT SCALE INDEX | 1.54 | Calculated, not typed. 1.00 = a 250-person, 3-day event with 6 months of planning. Doubling attendance moves it about 26%, not 100%.
4. STAFFING (headcount)
ONSITE — Managers | 3 | Onsite staff are costed PER PERSON — one line each on the P&L
ONSITE — Coordinators | 2
PRE-PLANNING — Managers | 1 | Pre-planning is costed BY CATEGORY. Headcount sets the weekly meeting rate and the workload check on the P&L.
PRE-PLANNING — Coordinators | 1
5. RATES
Manager — OUR COST / hr | 60 | Applies to every manager hour, pre-planning and onsite
Coordinator — OUR COST / hr | 42 | Applies to every coordinator hour, pre-planning and onsite
Manager — CLIENT RATE / hr (pre-planning) | 90
Coordinator — CLIENT RATE / hr (pre-planning) | 65
Manager — CLIENT RATE / hr (onsite) | 100
Coordinator — CLIENT RATE / hr (onsite) | 65
Overtime Multiplier | 1.5 | Coordinator overtime is billed and costed at 1.5x
6. ONSITE HOURS PER DAY
Manager hours per onsite day | 12 | Applied to event days + set-up days
Coordinator REGULAR hours per onsite day | 8 | Coordinators run 8 regular + 2 overtime on a normal show day
Coordinator OVERTIME hours per onsite day | 2
Hours per travel day | 8
7. OVERHEAD, FEES & DISCOUNTS
Staff Overhead per hour | 0.61 | Charged against every CTC staff hour. A cost to us — not billed.
Admin Fee % | 2% | 2% of the client subtotal, added to the client price. No cost against it.
Multi-Year Discount % | 5% | The '5% off additional years' line, off unless switched on below.
Apply Multi-Year Discount? | No
8. ONSITE ROLE TITLES
ONSITE MANAGERS |  | Only the first N lines are used, where N is the headcount in section 4. Titles are labels only — rates come from section 5.
Manager 1 | Project Manager
Manager 2 | Event Manager
Manager 3 | Executive Producer
Manager 4 | Registration Manager
Manager 5 | Housing / Expo Manager
Manager 6 | Production Manager
Manager 7 | Manager 7
Manager 8 | Manager 8
Manager 9 | Manager 9
Manager 10 | Manager 10
ONSITE COORDINATORS
Coordinator 1 | Event Coordinator
Coordinator 2 | Registration Coordinator
Coordinator 3 | Office Manager
Coordinator 4 | Production Assistant
Coordinator 5 | Exhibit Coordinator
Coordinator 6 | Housing Coordinator
Coordinator 7 | Coordinator 7
Coordinator 8 | Coordinator 8
Coordinator 9 | Coordinator 9
Coordinator 10 | Coordinator 10

## SCOPE
SCOPE OF WORK — matches the 2026 Master Proposal Template
Set INCLUDE? on every line. Hours calculate from the INPUTS tab; type a number into OVERRIDE HOURS to force a line. The P&L rolls these up to the top-level headings.
# | SCOPE OF WORK ITEM | TOP-LEVEL HEADING | STAFF | INCLUDE? | HOW THE HOURS ARE CALCULATED | CALC. HOURS | OVERRIDE HOURS | HOURS USED | CLIENT RATE | OUR RATE | CLIENT COST | OUR COST | TOP-LEVEL HEADING | HOURS | CLIENT COST | OUR COST | SEQ | STAFF
1 | PLANNING, TIMELINE & COMMUNICATIONS: Project Management System (ClickUp & Google Drive) | PLANNING, TIMELINE & COMMUNICATIONS | Coordinator | Yes | 1 hr per planning week | 39 |  | 39 | 65 | 42 | 2535 | 1638 | PLANNING, TIMELINE & COMMUNICATIONS | 125 | 12810 | 8436 | 1 | PM/EC
2 | PLANNING, TIMELINE & COMMUNICATIONS: Meetings, Minutes & Agendas | PLANNING, TIMELINE & COMMUNICATIONS | Team | Yes | 1 hr per planning week, whole team | 39 |  | 39 | 155 | 102 | 6045 | 3978 | VENUE SOURCING | 0 | 0 | 0
3 | PLANNING, TIMELINE & COMMUNICATIONS: Roles & Responsibilities | PLANNING, TIMELINE & COMMUNICATIONS | Manager | Yes | 5 x scale index | 8 |  | 8 | 90 | 60 | 720 | 480 | VENUE MANAGEMENT | 40 | 3600 | 2400 | 2 | PM
4 | PLANNING, TIMELINE & COMMUNICATIONS: Communication & Approvals | PLANNING, TIMELINE & COMMUNICATIONS | Manager | Yes | 1 hr per planning week | 39 |  | 39 | 90 | 60 | 3510 | 2340 | EVENT BRANDING | 45 | 4050 | 2700 | 3 | PM
5 | VENUE SOURCING: Request for Proposal | VENUE SOURCING | Manager | No | 6 x scale index | 9 |  | 9 | 90 | 60 | 0 | 0 | FOOD & BEVERAGE | 34 | 3060 | 2040 | 4 | PM
6 | VENUE SOURCING: Venue/Hotel Analysis | VENUE SOURCING | Manager | No | 6 x scale index | 9 |  | 9 | 90 | 60 | 0 | 0 | REGISTRATION | 82 | 5330 | 3444 | 5 | EC
7 | VENUE SOURCING: Site Visits | VENUE SOURCING | Manager | No | 10 hrs per site visit | 10 |  | 10 | 90 | 60 | 0 | 0 | SWAG BAG | 0 | 0 | 0
8 | VENUE SOURCING: Contract Negotiations | VENUE SOURCING | Manager | No | 5 x scale index | 8 |  | 8 | 90 | 60 | 0 | 0 | HOUSING LOGISTICS | 0 | 0 | 0
9 | VENUE MANAGEMENT: Venue Logistics | VENUE MANAGEMENT | Manager | Yes | 16 x scale index | 25 |  | 25 | 90 | 60 | 2250 | 1500 | THIRD PARTY VENDORS | 40 | 2600 | 1680 | 6 | EC
10 | VENUE MANAGEMENT: Meeting Space | VENUE MANAGEMENT | Manager | Yes | 10 x scale index | 15 |  | 15 | 90 | 60 | 1350 | 900 | STAFF MANAGEMENT | 14 | 1260 | 840 | 7 | PM
11 | EVENT BRANDING: Attendee Experience | EVENT BRANDING | Manager | Yes | 7 x scale index | 11 |  | 11 | 90 | 60 | 990 | 660 | VIP & PRESS LOGISTICS | 0 | 0 | 0
12 | EVENT BRANDING: Signage | EVENT BRANDING | Manager | Yes | 14 x scale index | 22 |  | 22 | 90 | 60 | 1980 | 1320 | SPONSORSHIPS | 32 | 2080 | 1344 | 8 | EC
13 | EVENT BRANDING: Décor | EVENT BRANDING | Manager | Yes | 8 x scale index | 12 |  | 12 | 90 | 60 | 1080 | 720 | SPEAKER MANAGEMENT | 0 | 0 | 0
14 | EVENT BRANDING: Graphic Design (add-on) | EVENT BRANDING | Manager | No | 26 x scale index | 40 |  | 40 | 90 | 60 | 0 | 0 | PROGRAMMING | 63 | 5670 | 3780 | 9 | PM
15 | FOOD & BEVERAGE: Food & Beverage Management | FOOD & BEVERAGE | Manager | Yes | 22 x scale index | 34 |  | 34 | 90 | 60 | 3060 | 2040 | RECEPTION PLANNING | 0 | 0 | 0
16 | REGISTRATION: Online Registration / Build-Out | REGISTRATION | Coordinator | Yes | 35 x scale index | 54 |  | 54 | 65 | 42 | 3510 | 2268 | FINANCIAL MANAGEMENT | 18 | 1620 | 1080 | 10 | PM
17 | REGISTRATION: Onsite Registration | REGISTRATION | Coordinator | Yes | 18 x scale index | 28 |  | 28 | 65 | 42 | 1820 | 1176 | EVENT MARKETING | 0 | 0 | 0
18 | REGISTRATION: Mobile App | REGISTRATION | Coordinator | No | 25 x scale index | 39 |  | 39 | 65 | 42 | 0 | 0 | EXHIBIT MANAGEMENT | 60 | 5400 | 3600 | 11 | PM
19 | SWAG BAG: Swag Bag Sourcing, Assembly & Distribution | SWAG BAG | Coordinator | No | 20 x scale index | 31 |  | 31 | 65 | 42 | 0 | 0 | POST-EVENT | 15 | 1350 | 900 | 12 | PM
20 | HOUSING LOGISTICS: Room Blocks | HOUSING LOGISTICS | Coordinator | No | 8 x scale index | 12 |  | 12 | 65 | 42 | 0 | 0 | TOURNAMENTS | 0 | 0 | 0
21 | HOUSING LOGISTICS: Housing Reports | HOUSING LOGISTICS | Coordinator | No | 4 x scale index | 6 |  | 6 | 65 | 42 | 0 | 0
22 | HOUSING LOGISTICS: Concession Management | HOUSING LOGISTICS | Coordinator | No | 3 x scale index | 5 |  | 5 | 65 | 42 | 0 | 0
23 | HOUSING LOGISTICS: Attendee Liaison | HOUSING LOGISTICS | Coordinator | No | 5 x scale index | 8 |  | 8 | 65 | 42 | 0 | 0
24 | HOUSING LOGISTICS: Overflow Hotel Sourcing | HOUSING LOGISTICS | Coordinator | No | 3 x scale index | 5 |  | 5 | 65 | 42 | 0 | 0
25 | THIRD PARTY VENDORS: Vendors | THIRD PARTY VENDORS | Coordinator | Yes | 5 hrs per vendor sourced | 25 |  | 25 | 65 | 42 | 1625 | 1050
26 | THIRD PARTY VENDORS: Photographer / Videographer | THIRD PARTY VENDORS | Coordinator | Yes | 10 x scale index | 15 |  | 15 | 65 | 42 | 975 | 630
27 | STAFF MANAGEMENT: Temporary Staff | STAFF MANAGEMENT | Manager | Yes | 5 x scale index | 8 |  | 8 | 90 | 60 | 720 | 480
28 | STAFF MANAGEMENT: Volunteers | STAFF MANAGEMENT | Manager | Yes | 4 x scale index | 6 |  | 6 | 90 | 60 | 540 | 360
29 | VIP & PRESS LOGISTICS: VIPs | VIP & PRESS LOGISTICS | Coordinator | No | 12 x scale index | 18 |  | 18 | 65 | 42 | 0 | 0
30 | VIP & PRESS LOGISTICS: Press Logistics | VIP & PRESS LOGISTICS | Coordinator | No | 8 x scale index | 12 |  | 12 | 65 | 42 | 0 | 0
31 | SPONSORSHIPS: Sponsorship Opportunities | SPONSORSHIPS | Coordinator | Yes | 8 x scale index | 12 |  | 12 | 65 | 42 | 780 | 504
32 | SPONSORSHIPS: Sponsor Management | SPONSORSHIPS | Coordinator | Yes | 1 hr per sponsor | 20 |  | 20 | 65 | 42 | 1300 | 840
33 | SPEAKER MANAGEMENT: Speaker Prep | SPEAKER MANAGEMENT | Coordinator | No | 0.7 hrs per speaker | 11 |  | 11 | 65 | 42 | 0 | 0
34 | SPEAKER MANAGEMENT: Speaker Management Onsite | SPEAKER MANAGEMENT | Coordinator | No | 0.3 hrs per speaker | 5 |  | 5 | 65 | 42 | 0 | 0
35 | PROGRAMMING: Audio Visual | PROGRAMMING | Manager | Yes | 18 x scale index | 28 |  | 28 | 90 | 60 | 2520 | 1680
36 | PROGRAMMING: Stage Production | PROGRAMMING | Manager | Yes | 15 x scale index | 23 |  | 23 | 90 | 60 | 2070 | 1380
37 | PROGRAMMING: Entertainment & Talent | PROGRAMMING | Manager | Yes | 8 x scale index | 12 |  | 12 | 90 | 60 | 1080 | 720
38 | PROGRAMMING: Recording & Broadcast — Pre-Event Coordination | PROGRAMMING | Manager | No | 8 x scale index | 12 |  | 12 | 90 | 60 | 0 | 0
39 | PROGRAMMING: Recording & Broadcast — Onsite Support | PROGRAMMING | Manager | No | 10 x scale index | 15 |  | 15 | 90 | 60 | 0 | 0
40 | RECEPTION PLANNING: Concept & Strategy | RECEPTION PLANNING | Coordinator | No | 3 x scale index | 5 |  | 5 | 65 | 42 | 0 | 0
41 | RECEPTION PLANNING: Venue & Layout | RECEPTION PLANNING | Coordinator | No | 4 x scale index | 6 |  | 6 | 65 | 42 | 0 | 0
42 | RECEPTION PLANNING: Food & Beverage | RECEPTION PLANNING | Coordinator | No | 4 x scale index | 6 |  | 6 | 65 | 42 | 0 | 0
43 | RECEPTION PLANNING: Entertainment & Atmosphere | RECEPTION PLANNING | Coordinator | No | 3 x scale index | 5 |  | 5 | 65 | 42 | 0 | 0
44 | RECEPTION PLANNING: Guest Experience | RECEPTION PLANNING | Coordinator | No | 3 x scale index | 5 |  | 5 | 65 | 42 | 0 | 0
45 | RECEPTION PLANNING: Staffing & Logistics | RECEPTION PLANNING | Coordinator | No | 3 x scale index | 5 |  | 5 | 65 | 42 | 0 | 0
46 | RECEPTION PLANNING: Capture & Follow-Up | RECEPTION PLANNING | Coordinator | No | 2 x scale index | 3 |  | 3 | 65 | 42 | 0 | 0
47 | FINANCIAL MANAGEMENT: Budgets, Reporting & Billing | FINANCIAL MANAGEMENT | Manager | Yes | 12 x scale index | 18 |  | 18 | 90 | 60 | 1620 | 1080
48 | EVENT MARKETING: Strategy & Timeline | EVENT MARKETING | Manager | No | 8 x scale index | 12 |  | 12 | 90 | 60 | 0 | 0
49 | EVENT MARKETING: Social Media & Email Campaigns | EVENT MARKETING | Manager | No | 9 x scale index | 14 |  | 14 | 90 | 60 | 0 | 0
50 | EVENT MARKETING: Messaging | EVENT MARKETING | Manager | No | 5 x scale index | 8 |  | 8 | 90 | 60 | 0 | 0
51 | EVENT MARKETING: Marketing Assistance | EVENT MARKETING | Manager | No | 5 x scale index | 8 |  | 8 | 90 | 60 | 0 | 0
52 | EXHIBIT MANAGEMENT: Exhibitor Planning & Onsite Execution | EXHIBIT MANAGEMENT | Manager | Yes | 1 hr per exhibitor | 60 |  | 60 | 90 | 60 | 5400 | 3600
53 | POST-EVENT: Debrief, Reporting & Recommendations | POST-EVENT | Manager | Yes | 10 x scale index | 15 |  | 15 | 90 | 60 | 1350 | 900
54 | TOURNAMENTS: Venue Booking & Coordination | TOURNAMENTS | Coordinator | No | 7 x scale index | 11 |  | 11 | 65 | 42 | 0 | 0
55 | TOURNAMENTS: Registration & Communications | TOURNAMENTS | Coordinator | No | 8 x scale index | 12 |  | 12 | 65 | 42 | 0 | 0
56 | TOURNAMENTS: Check-In & Onsite Management | TOURNAMENTS | Coordinator | No | 7 x scale index | 11 |  | 11 | 65 | 42 | 0 | 0
| TOTAL — INCLUDED SCOPE | [6 empty] | 568 |  |  | 48830 | 32244

## HOW TO USE
HOW TO BUILD A NEW CONFERENCE P&L
STEP 1 — INPUTS
• Event size: attendees, exhibitors, sponsors, speakers, vendors to source, site visits.
• Schedule: event days, set-up days, travel days, months of pre-planning.
• Staffing: how many managers and coordinators onsite, and how many in pre-planning.
• Rates are pre-set — manager $60/hr cost, coordinator $42/hr cost. Change only if the rate card changes.
STEP 2 — SCOPE
• Every line matches the Master Proposal Template, sub-item by sub-item. Set INCLUDE? to Yes or No on each.
• Hours calculate automatically. Disagree with a line? Type your number into OVERRIDE HOURS — nothing else changes.
STEP 3 — P&L
• Nothing to type. Scope rolls up to the top-level proposal headings, so the P&L reads the same way the proposal does.
• Watch HRS / PERSON / WEEK — above roughly 10 the headcount is too thin for the scope.
THE EVENT SCALE INDEX
• Most scope lines are priced as a base weight multiplied by the Event Scale Index, shown on INPUTS. The index is:
• (attendees / 250) ^ 1/3 x (planning months / 6) ^ 1/2 x (event days / 3) ^ 1/4
• An index of 1.00 is a 250-person, 3-day event with 6 months of planning. The cube and square roots matter: doubling attendance raises the index about 26%, not 100%, which is how our hours have actually behaved. Straight percentage-of-attendees rules break down badly at 1,000+ people.
• Lines with a real count behind them skip the index and bill directly: exhibitors x 1 hr, sponsors x 1 hr, speakers x 1 hr, vendors x 5 hrs, site visits x 10 hrs. Weekly items — meetings, the project management system, approvals — bill 1 hour per planning week.
HOW THE MONEY WORKS
• CLIENT COST = hours x client rate. Pre-planning: manager $90 / coordinator $65. Onsite: manager $100 / coordinator $65. Coordinator overtime bills at 1.5x.
• OUR COST = hours x our rate. Manager $60, coordinator $42, overtime 1.5x.
• STAFF OVERHEAD = $0.61 x every CTC staff hour, pre-planning and onsite. A cost to us, not billed, so it reduces margin.
• ADMIN FEE = 2% of the client subtotal, added to what the client pays. Nothing costs against it, so all of it is profit.
• MULTI-YEAR DISCOUNT = the 5% off additional years. Off by default — switch it on at the bottom of INPUTS section 7.